## Assumptions
Childs Game Project |  |  | Assumptions
ID | Date raised | Raised by | Assumption | Validated (Y/N | Open/Closed | Impact | Comment / Linked Risk/Issue
A_001 | 2022-07-28 | Ian Wolloff | The August 2022 release date allows enough time for the development | N | Closed | Starting later can be accommodated | Risk R001 raised
A_002 | 2022-07-28 | Ian Wolloff | Code produced is of the correct quality | N | Closed | Large number/low quality will slow us up | Risk R002 raised
A_003 | 2022-07-28 | Ian Wolloff | There are no electrical shutdowns during any key working periods | N | Closed | Cant work | Risk R005 raised
A_004 | 2022-07-28 | Ian Wolloff | There are no major incidents which impact any of the project resources | N | Closed | Resourced pulled to other tasks | Risk R006 raised
A_005 | 2022-07-28 | Ian Wolloff | Resources are available - no sickness or impacting leave | N | Closed | Team over stretched | Risk R007 raised
A_006 | 2022-07-28 | Ian Wolloff | Work doesn't over run | N | Closed | Production work the following working day delayed | Risk R008 raised
A_007 | 2022-07-28 | Ian Wolloff | Dates are co-ordinated satisfactorily with server maintenance works | Y | Closed | Weekend working or processes restricted during period | Risk R009 raised
A_008 | 44770 | Ian Wolloff | There are no or minimal changes to Child Game Requirments | N | Open | Increased workload during Delivery Phase
A_009 | 2022-07-28 | Ian Wolloff | Project management processes used are based on best practice | N | Closed | Project Non Managed in Best Way

## Dependencies
Year End 2021_22 |  |  | Dependencies
ID | Date raised | Raised by | Dependency | Scheduled Date | Completion Date | Impact | Resolution
D_001 | 2021-10-15 | Ian Wolloff | Development Team has access to tooling required for project delivery | 2022-01-07 | 2022-12-21 | Without correct tooling deveopers will be unable to create quality applications | Ensure that all developers can access the tools they require either through the student GitHub program or from opensource tooling (Spider etc)
D_002 | 2021-10-15 | Ian Wolloff | Web Servers and Cloud Storage setup | 2022-06-26 | 2022-07-05 | Without backend Services developers will be unable to deploy the applciation. | IW will arange for backend servers to be stood up as a prority so backend is avaiable before the application code has been deveoped.
D_003 | 2021-11-02 | Ian Wolloff | Google Docs | 2022-06-26 | 2022-06-26 | Gives Team ability to share docuemnts | IW will arange for a google docs area to be setup and for team members to be given access.

## Risks
Risk ID | Date Identified | Raised by: | Risk Title | Description of Risk (there is a risk that….) | Impact (resulting in….) | Owner | Initial |  |  | Response (Avoid, Reduce, Transfer, Contingency, Accept) | PROXIMITY | Control Measures/ Comments | Controlled |  | Control Score | Status | Date of last review | Likelihood | Delay in Months | Monthly Run Rate | Total Cost of Risks
[7 empty] | Probability | Impact | Risk Score |  | WITHIN 1 MONTH 1 - 3 MONTHS 3 MONTHS + |  | Probability | Impact | [6 empty] | 0
[20 empty] | Cost | Cost Rationale
R_002 | 2022-07-01 | Project risk | Quality of releases | There is a risk that: Due to limited Python development experence that the code produced will not be of the quality required. | Resulting in: Additional in-house effort for testing the additional eleases. |  | 3 | 3 | 9 | Accept | 1 - 3 Months | Use of Code Quality tools can limit the impact though there is no substute for real world experience so we will need to monitor the quality of the code being produced. | 2 | 3 | 6 | OPEN | 20.08.2022
R_004 | 2022-07-25 | IW | COVID19 | There is a risk that: Memebers of the team may be unable to fully take part in project tasks due to exposure to COVID 19 | Resulting in: Resourcing work becomes an issue |  | 3 | 3 | 9 | Reduce | 1 - 3 Months | impact understood and being managed | 3 | 2 | 6 | OPEN | 22.08.2022
R_005 | 2021-10-15 | Annual risk | Planned Electrical Shutdowns | There is a risk that: Any planned shutdowns could restrict staff's access to the Civic offices | Resulting in: Planned work cannot take place |  | 2 | 3 | 6 | Avoid | 1 - 3 Months | Make contact with Facilities Management and advise to avoid key weekends; coordinated through Forward Schedule of Change (FSC) | 1 | 3 | 3 | OPEN | 2022-02-18
R_006 | 2021-10-15 | Annual risk | Major incident | There is a risk that: A major incident may occur that disables PCC infrastructure. | Resulting in: Delay and impact to either testing or live work. |  | 2 | 4 | 8 | Accept | 1 - 3 Months | If this occurs then the project will need to fit in to the Business continuity plan and reschedule resources as far as possible. | 1 | 4 | 4 | OPEN | 2022-02-18
R_007 | 2022-08-02 | Project risk | Team Sickness/Absence | There is a risk that: Team sickness or absence may occur during parts of the Game Project | Resulting in: Delay in work required or additional work necessary to achieve deadlines. |  | 3 | 4 | 12 | Contingency | 1 - 3 Months | Additional IT resources have been identified for the project from the existing team members though this may affect the devivery due to only having resources from a small pool. | 3 | 2 | 6 | OPEN | 2022-08-18
R_008 | 2021-10-15 | Annual risk | Weekend work over-run | There is a risk that: Issues with LAHRA/HB uprating, Council Tax/HB/NNDR or HB Subsidy claim run weekend work mean that it is not completed within the weekend and has to be carried over to the Monday morning | Resulting in: Delay in completion of required tasks, user access to Live needs to be restricted until this is complete |  | 2 | 3 | 6 | Contingency | 1 - 3 Months | Probability to be reduced by testing to firm up timings and highlight any potential problem areas as early as possible so they can be mitigated. | 1 | 4 | 4 | OPEN | 2022-02-18
R_009 | 2021-10-15 | Annual risk | Clash with planned IT or other maintenance weekends | There is a risk that: Weekends scheduled for Rent/HB/Council tax uprating and year-end roll-over conflict with scheduled downtime for IT maintenance | Resulting in: Delay in work required or additional overtime necessary to achieve deadlines. |  | 2 | 2 | 4 | Avoid | 1 - 3 Months | PM to coordinate with Facilities and IT Change Manager 22/12 - Year End activities reported and recorded in the IT Change Schedule. Change Manager attends Year_End team meetings to highlight any conflict | 1 | 2 | 2 | OPEN | 2022-02-18
R_010 | 2021-10-15 | Annual risk | Council Tax & NNDR rollover | There is a risk that: Problems will be encountered with the year-end rollover | Resulting in: Delay in verification and sign-off by Northgate with the knock-on effect of system downtime |  | 2 | 4 | 8 | Reduce | 1 - 3 Months | Retained from previous years EOY risk log. There will be reduced time to resolve any issues without impacting batch processing and to avoid downtime | 2 | 2 | 4 | OPEN | 2022-02-18
R_011 | 2021-10-15 | Annual risk | End of Year Database | There is a risk that: The end of year database (used by Housing to manage / implement Year End Changes) will not be completed and tested in time for the year end work required. | Resulting in: Extra work/resource required to complete and test |  | 2 | 2 | 4 | Reduce | 1 - 3 Months | Developer resource to be allocated this year | 1 | 2 | 2 | OPEN | 2022-02-18
R_013 | 2021-10-15 | SC | Hardware failure | There is a risk that: The existing hardware platform fails in some way, including slowing of performance | Resulting in: Delay to planned works |  | 1 | 4 | 4 | Reduce | 1 - 3 Months | Hardware platform is monitored and maintained year round, failure can never be completely excluded as a risk 5/1 - Additional NEC support purchased for EOY period | 1 | 4 | 4 | OPEN | 2022-02-18
Note on P1: IAW PCC Risk Management Strategy: 1-2 = Very Low (Green) 3-4 = Low (Yellow) 6-9 = Medium (Orange) 12-16 = High (Red)
Note on H2: 1 = Very Unlikely 2 = Unlikely 3 = Likely 4 = Very Likely
Note on I2: 1 = Minor 2 = Significant 3 = Serious 4 = Major
Note on J2: IAW PCC Risk Management Strategy: 1-2 = Very Low (Green) 3-4 = Low (Yellow) 6-9 = Medium (Orange) 12-16 = High (Red)
Note on N2: 1 = Very Unlikely 2 = Unlikely 3 = Likely 4 = Very Likely
Note on O2: 1 = Minor 2 = Significant 3 = Serious 4 = Major

## Issues
Issue ID | Date Identified | Raised by: | Issue Title | Issue Type (Delivery, Resource, Migration etc.) | Description | Owner | Priority (1-5) | Comments/ Resolution | Status (Open/Closed) | Date of last review
I_001 | 2022-07-07 | Ian Wolloff | Web Server Unable to update docker image from private registry | Delivery | DBA availability and capacity from December | IW | 1 | GitHub PAT Token permission did not give the correct permissions to access the container registry new token issued and problem now resolved and the watchtower service can pull images from github | closed | 2022-08-23

## Risks - not project specific
Risk ID | Date Identified | Raised by: | Risk Title | Description of Risk (there is a risk that….) | Impact (resulting in….) | Owner | Initial (Scoring 1-4) |  |  | Response (Avoid, Reduce, Transfer, Contingency, Accept)) | PROXIMITY | Control Measures (Uncontrolled, Partially Controlled, Controlled) | Controlled |  | Control Score | Status | Date of last review
[7 empty] | Probability | Impact | Risk Score (Prob x Impact) |  | WITHIN 1 Week 1 - 3 Weeks 3 Weeks + |  | Probability | Impact
___ R-001 | 2022-07-14 | IW | Act of God | Earthquake, Tsunami, pandemic, Flood, sink hole | Delays to works | PM | 1 | 4 | 4 | Accept, nothing we can do about it | Anytime | Uncontrolled. Re-examine deadlines if something like this occurs. Ensure all key stakeholders are advised asap if this happens. | 1 | 4 | 4 | Open | 22.08.2022
___ R-002 | 2022-07-14 | IW | Civil unrest | Riot, protest, occupation | Delays to works | PM | 1 | 3 | 3 | Reduce - monitor and plan if events develop | Anytime | Uncontrolled. Re-examine deadlines if something like this occurs. Monitor media and Corporate communications for possibilities. Plan accordingly if necessary | 1 | 3 | 3 | Open | 22.08.2022
___ R-003 | 2022-07-14 | IW | Terrorist Act | Bomb, hostage, violence | Delays to works | PM | 1 | 3 | 3 | Accept, nothing we can do about it | Anytime | Uncontrolled. Re-examine deadlines if something like this occurs. Ensure all key stakeholders are advised asap if this happens. | 1 | 3 | 3 | Open | 22.08.2022
___ R-004 | 2022-07-14 | IW | Extreme weather | Heat, cold, snow, rain | Delays to works - works period includes summer, winter? | PM | 1 | 3 | 3 | Reduce - monitor and plan if events develop | Check project programme | Uncontrolled. Ensure key staff have VPN access in case bad weather keeps them at home/closes the Civic. | 1 | 2 | 2 | Open | 22.08.2022
___ R-005 | 2022-07-14 | IW | Industrial Action (internal or external) | External staff action - e.g. Data Centre Staff etc | Delays to works | PM | 1 | 3 | 3 | Reduce - monitor and plan if events develop | 1 - 3 Weeks | Uncontrolled. Re-examine deadlines if something like this occurs. Monitor media and Corporate for possibilities. Plan accordingly if necessary | 1 | 2 | 2 | Open | 22.08.2022
___ R-006 | 2022-07-14 | IW | Seasonal Holidays | Time is lost to the project | Delays to works | PM | 4 | 1 | 4 | ensure cover over these periods | tbc | Partially controlled. Plan holidays and project development together. | 4 | 1 | 4 | Open | 22.08.2022
___ R-007 | 2022-07-14 | IW | illness | flu and illness outbreaks | Unavailability of team | PM | 3 | 3 | 9 | Reduce/Accept | Anytime | Flu / Covid vaccination | 3 | 3 | 9 | Open | 22.08.2022
Note on P1: IAW PCC Risk Management Strategy: 1-2 = Very Low (Green) 3-4 = Low (Yellow) 6-9 = Medium (Orange) 12-16 = High (Red)
Note on H2: 1 = Very Unlikely 2 = Unlikely 3 = Likely 4 = Very Likely
Note on I2: 1 = Minor 2 = Significant 3 = Serious 4 = Major
Note on J2: IAW PCC Risk Management Strategy: 1-2 = Very Low (Green) 3-4 = Low (Yellow) 6-9 = Medium (Orange) 12-16 = High (Red)
Note on N2: 1 = Very Unlikely 2 = Unlikely 3 = Likely 4 = Very Likely
Note on O2: 1 = Minor 2 = Significant 3 = Serious 4 = Major

## Risk Key
Risk Scoring
The scoring of risks is in accordance with Team Twos risk management strategy as follows:
Probability
1 | Very Unlikely
2 | Unlikely
3 | Likely
4 | Very Likely
Impact
1 | Minor
2 | Significant
3 | Serious
4 | Major
Risk Score
The overall risk score is given as the impact multiplied by the probability:
1-2 | Very Low
3-4 | Low
6-9 | Medium
12-16 | High

## Closed Risks
Risk ID | Date Identified | Raised by: | Risk Title | Description of Risk (there is a risk that….) | Impact (resulting in….) | Owner | Initial |  |  | Response (Avoid, Reduce, Transfer, Contingency, Accept) | PROXIMITY | Control Measures/ Comments | Controlled |  | Control Score | Status | Date Closed
[7 empty] | Probability | Impact | Risk Score |  | WITHIN 1 Week 1 - 3 Weeks 3 Weeks + |  | Probability | Impact
R_001 | 2021-07-15 | Project Risk | Late delivery | There is a risk that: Developemnt of the solution may not be completed in the agreed timeframe. | Resulting in: Delays to testing timeframes and reduced availability of resources within timeframes required | IW | 3 | 3 | 9 | Accept | 1 - 3 Weeks | Regular communication with development team and customers to ensure that timeframes are reliastic and can be met with the amount of allocated resource. | 3 | 2 | 6 | closed | 2021-12-22
R_003 | 2021-07-15 | IW | COVID19 | There is a risk that: Members of the development / management team may get Covid | Resulting in: Restricted ability to work on the solution while recovering from COVID infection affecting the delivery timeline | IW | 3 | 2 | 6 | Reduce | 1 - 3 Weeks | Covid Boosters and General Covid Safe procedures should reduce though not elimiate this risk to the project. | 2 | 2 | 4 | OPEN | 2022-01-05
R_012 | 2021-07-15 | Project Risk | Equipment Failure | There is a risk that: The Servers hosting the solution in the Team II DataCentre may break. | Resulting in: Delay in being able to Provide the solution | IW | 1 | 4 | 4 | Reduce | 3 Weeks + | Infrastructre has been tested so the likelyhood of a failure is remote if this does happen then we will failover to Azure or AWS hosted servers and update the public DNS record to point to the new location | 1 | 2 | 2 | OPEN | 2022-01-05
R_016 | 2021-07-24 | IW | Programme resource conflict | There is a risk that: There are insufficient Team 2 resources to support Year End activities for the Devepoment of the Child Game | Resulting In: Delays to testing and impact to the delivery timelines | IW | 3 | 3 | 9 | Avoid | 3 Weeks + | With Team members taking on multiple roles there is a risk that there will be conflict where the same team meber needs to do multiple work items at the same time | 3 | 2 | 6 | OPEN | 2022-02-18
[9 empty] | 0 | [5 empty] | 0 | OPEN
[9 empty] | 0 | [5 empty] | 0 | OPEN
[9 empty] | 0 | [5 empty] | 0 | OPEN
Note on P1: IAW PCC Risk Management Strategy: 1-2 = Very Low (Green) 3-4 = Low (Yellow) 6-9 = Medium (Orange) 12-16 = High (Red)
Note on H2: 1 = Very Unlikely 2 = Unlikely 3 = Likely 4 = Very Likely
Note on I2: 1 = Minor 2 = Significant 3 = Serious 4 = Major
Note on J2: IAW PCC Risk Management Strategy: 1-2 = Very Low (Green) 3-4 = Low (Yellow) 6-9 = Medium (Orange) 12-16 = High (Red)
Note on N2: 1 = Very Unlikely 2 = Unlikely 3 = Likely 4 = Very Likely
Note on O2: 1 = Minor 2 = Significant 3 = Serious 4 = Major

## Closed Issues
Issue ID | Date Identified | Raised by: | Issue Title | Issue Type | Description | Owner | Priority (1-5) | Comments/ Resolution | Status (Open/Closed) | Date Closed
I_001 | 2022-07-07 | Ian Wolloff | Web Server Unable to update docker image from private registry | Delivery | DBA availability and capacity from December |  | 1 | GitHub PAT Token permission did not give the correct permissions to access the container registry new token issued and problem now resolved and the watchtower service can pull images from github | closed | 2022-08-23